SETMIS WORKSHOP ACTION LIST

TIME	: 	08:00 – 13:40

DATE	: 	20 July 2018

VENUE:	MQA Offices

| ACTION | RESPONSIBILITY | TIMELINE | Progress |
| --- | --- | --- | --- |
| - SETAs that are behind with their data submission to submit all outstanding data on the system. | SETAs | 1 August 2018 – 28 September 2018 | - Letters sent to SETAs on 08 August 2018 requesting written responses from SETAs with regards to their failure to upload their 2018/19 first quarterly reports through the SETMIS system |
| - Engage with SETA on their availability for the Information System Coordination Directorate (ISCD) team to provide data submission systemic challenges to SETMIS – Priority is to focus firstly on the SETAs that have not made any submissions to date. | Directorate: SPM - Sector Liaison Managers | 27 July 2018 | - Dates were requested form SETA through their Sector Liaison Managers. |
| - Compile a SETA visitation schedule. Furnish the visitation schedule to the ISCD support team for their attention and action. | Directorate: SPM | 31 July 2018 | - Dates shared with ISCD support team. - Dates were confirmed by the ISDC Team - SETA visitation are currently being conducted by the ISCD support team. |
| - Provide assistance to SETAs on EDUktiV data validation utility challenges such as: - installation/update; - configuration; - validation; and - generic application utilisation. | Branch P | 1 August 2018 – 15 September 2018 | - Installation, configuration validation and application utilisation was successfully conducted (on site) on the users operating system for the following SETAs: - W&RSETA - MICTSETA - CATHSETA - MICT - CHIETA - TETA - FP&MSETA - It was reported on site that installation and configuration of EDUktiV Data validation and submission tool was not necessary to be conducted as there were no challenges reported in doing so by the following SETAs: - SERVICESSETA - ETDP SETA - FOODBEV - MERSETA - Installation finalisation for AGRISETA to executed on Thursday, 16 August 2018. - Installation could not be finalised – AgriSETA IT will proceed in finalising the installation. - LGSETA to finalise the installation execution as they indicated that they prefer processing at the server location. LGSETA-IT officials to provide DHET confirmation when a successful installation done. Otherwise, if required, ISCD support team to provide further technical support in this regard. |
| - Concepts and definitions to be sent to SETAs for inputs | Branch P | 30 July 2018 | - Concepts and definitions document shared by Branch on 23 July 2018 to be sent out for input to SETAs by Branch P, the document was with workshop attendees for input by Branch S. |
| - Provide inputs on concepts and definitions utilisation within the SETMIS context. | SETAs | 10 August 2018 | - Follow up was made by Branch S on 13 August 2018. - No inputs received from the SETAs. |
| - At the next workshop, DHET to make a presentation on the data submission results. This will provide SETAs a holistic depiction status at a national level on the progress made on data submission compliance and declaration to SETMIS. | Branch P | November 2018 |  |
| - Compile necessary supplementary workshop pack. | Branch P | November 2018 | - As one of the SETAs that is currently beginning to smoothly conduct data submission with much better ease, a request was made at the SETMIS end-user support meeting conducted on Wednesday, 15 August 2018 to both the service provider and the SETA to avail themselves and prepare brief presentations. - Mainly to demonstrate on how to navigate through data mapping/alignment as well as correcting possible errors detected both at the data validation and feedback receipt from DHET correction level. - Ms Avan Brakel, and Ms Andisiwe Ganjana have agreed to avail themselves for the next SETMIS workshop to be held in November 2018. - The main objective of this exercise is to incorporate best practices amongst the SETAs as well as the Service provides so they can learn from one another. |
| 8.1. Draft and disseminate invitation letters to both Ms Avan Brakel, Solugrowth service provider and Ms Andiswa Ganjana, CATHSSETA data manager respectively, to prepare presentations on best practice in conducting SETMIS data mapping/alignment and possible error correction implementation. | Branch S | Wednesday, 22 August 2018 | - A letter addressed to the CEO of CATHSSETA regarding inviting the institution’s data manager as well as the service provider in response to item 8 has been drafted, signed and disseminated on Friday, 31 August 2018 at 5:19 PM. |
| - ISCD support team to prepare and upload SETMIS data related online YouTube videos in relation to providing support material for reference on challenges such as EDUktiV installation/update, configuration, validation and generic utilisation. | Branch P | August 2018 | - The first SETMIS EDUktiV data validation and submission video has been completed. - This video describes how to conduct a SETMIS data validation and submission using EDUktiV utility from the beginning to the end for first-time users. - Viewing and dissemination of video is current underway at the current ongoing SETA technical support site visits. - This video is now available on YouTube for download. It can be downloaded on the following URL address: https://www.youtube.com/playlist?list=PLKbyUCvlM-K76yelgfIxb2R1_CDq8v7T8 |
| - ISCD support team to notify Branch S on the availability of the uploaded online support material in order for the branch to communicate with the stakeholders accordingly. | Branch P | August 2018 | - End-user support video on how to conduct a successful SETMIS data validation and submission using EDUktiV utility available. - The video to be downloaded as of Wednesday, 15 August 2018 by clicking the URL provided in item 9 |
| - Inform SETAs to download online support material for information and/or utilisation purposes. | Branch S | August 2018 |  |
| - Send feedback report whether all information was submitted. | Branch P | 31 October 2018 | - Progress report on SETAs technical support site visit is currently be conducted via an email to both Branch P and Branch S officials on a regular basis. |
| - Check the whole specification and determine which fields should be made optional and compulsory for loading on SETMIS | Branch S | 16 August 2018 |  |
| - Provide clarity on reporting of artisans (some SETAs report them under learnerships) and where part-qualifications are supposed to be captured. | Branch S and Branch P | 16 August 2018 | - Clarity is currently been provided accordingly at the site visits that are under way as part of the technical SETMIS support. |
| - Update the database of schools (some schools are not in the database). | Branch P | 31 August 2018 | - The database is downloadable in Excel from the Department of Basic Education (DBE) website. The ISCD support team is currently in a process of integrating the schools database into SETMIS. |
| - Provide clarity on when will the manual reporting of SETA data be phased out as well as providing a cut-off date. | Branch S and Branch P | 31 October 2018 | Agenda item |
| - ISCD support team to determine on whether to relax or enforce some of the rules in the system on the provider file and provide feedback on this regard. | Branch P | 31 August 2018 | - The provider file is important and all data fields are required, accordingly, these are also marked as required. The only compromise made, was to add the employer as a provider with the type employer. |